## Project Planner
Sprint 3 - Agility
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | STAFF MEMBER(S) | PLAN START (Hours) | PLAN DURATION (Hours) | ACTUAL START (Hours) | ACTUAL DURATION (Hours) | PERCENT COMPLETE | HOURS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Develop a plan (Gantt chart) | Aidan, Jason, Bryan | 1 | 1 | 1 | 1 | 100% | HOURS 1: actual
Build requirements table | Aidan, Jason, Bryan | 2 | 1 | 2 | 1 | 100% | HOURS 2: actual
Requirements signoff table | Aidan, Jason, Bryan | 3 | 2 | 3 | 1 | 100% | HOURS 3: actual; HOURS 4: plan
Create an Algorithm | Jason | 5 | 3 | 4 | 2 | 100% | HOURS 4: actual; HOURS 5: actual; HOURS 6: plan; HOURS 7: plan
Create a Flowchart | Bryan | 8 | 2 | 6 | 2 | 100% | HOURS 6: actual; HOURS 7: actual; HOURS 8: plan; HOURS 9: plan
Create Block Code | Jason | 10 | 4 | 8 | 3 | 100% | HOURS 8: actual; HOURS 9: actual; HOURS 10: actual; HOURS 11: plan; HOURS 12: plan; HOURS 13: plan
Sensor data diagram | Aidan | 14 | 1 | 11 | 1 | 100% | HOURS 11: actual; HOURS 14: plan
Test Table | Aidan, Jason, Bryan | 15 | 2 | 12 | 2 | 100% | HOURS 12: actual; HOURS 13: actual; HOURS 15: plan; HOURS 16: plan
Staffing Plan | Aidan, Jason, Bryan | 17 | 1 | 14 | 2 | 100% | HOURS 14: actual; HOURS 15: actual; HOURS 17: plan
System Design Document | Aidan, Jason, Bryan | 18 | 4 | 16 | 4 | 100% | HOURS 16: actual; HOURS 17: actual; HOURS 18: actual; HOURS 19: actual; HOURS 20: plan; HOURS 21: plan
Robot Video | Bryan | 22 | 2 | 20 | 3 | 100% | HOURS 20: actual; HOURS 21: actual; HOURS 22: actual; HOURS 23: plan
Github Repository | Jason | 24 | 1 | 23 | 2 | 100% | HOURS 23: actual; HOURS 24: actual
Robot Performance Test | Aidan, Jason, Bryan | 25 | 2 | 25 | 2 | 100% | HOURS 25: actual; HOURS 26: actual